## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
all | implement base project | 0.75 | 0
add a film to my watch collection | Implement UI modal for films | 3 | 0
| Implement add watched film methods | 1 | 0
add a series to my watch collection | Implement UI modal for series | 1 | 0
| Implement add watched series methods | 0.5 | 0
See my previously watch film or series | Implement UI for previously watched | 1.5 | 0
| Implement watched list classes | 0.5 | 0.5 | 0
add a rating to a watched film or series | Modify the UI of the modals | 0.5 | 0.5 | 0
| Implement the rating methods | 0.75 | 0.75 | 0
| Modify the UI of the list | 0.5 | 0.5 | 0
add a description to a watched film or series | Modify the UI of the modals | 0.5 | 0.5 | 0
| Implement the description methods | 0.5 | 0.5 | 0
| Modify the UI of the list | 0.5 | 0.5 | 0
add a film to my watch list | Create the UI for what I have to watch | 1 | 1 | 1 | 0
| Implement add film to whish list method | 1 | 1 | 1 | 0
mark a film or series as watched | Modify the UI to add a button to remove this film or series | 0.5 | 0.5 | 0.5 | 0
| Automaticly open & pre-fill the add film or series modals | 1 | 1 | 1 | 0
| Delete it from the whish list if mark as watched | 0.75 | 0.75 | 0.75 | 0
| Estimate Totals | 15.75 | 8 | 4.25 | 0 | 0